## Parameters
Deterministic Flow Shop — Base Processing Times (minutes)
Module Type | Area (m²) | Framing | MEP | Finishing | Inspection
Type A | 4.3 | 67 | 178 | 155 | 44
Type B | 7.9 | 225 | 599 | 524 | 150
Type C | 9.9 | 353 | 941 | 823 | 235
Mix per floor: | 8 × Type A, 2 × Type B, 7 × Type C = 17 modules/floor
Project: | 6 floors × 17 = 102 modules
Working day: | 480 minutes (8 hours) — used to convert minutes → days
Stage: | DETERMINISTIC (no variability, no disruptions). CV = 0 at this stage.
orderings tested (each repeated 6 times, once per floor):
Base Line | 8A → 2B → 7C

## Ord1_8A-2B-7C
Ordering 1: 8A-2B-7C (this block order repeated for all 6 floors)
Seq # | Floor | Type | p_Framing | p_MEP | p_Finish | p_Insp | C_Framing | C_MEP | C_Finish | C_Insp
1 | 1 | Type A | 67 | 178 | 155 | 44 | 67 | 245 | 400 | 444 | RESULTS (minutes)
2 | 1 | Type A | 67 | 178 | 155 | 44 | 134 | 423 | 578 | 622 | Makespan (days) | 117.4562
3 | 1 | Type A | 67 | 178 | 155 | 44 | 201 | 601 | 756 | 800
4 | 1 | Type A | 67 | 178 | 155 | 44 | 268 | 779 | 934 | 978 | Floor completion (min)
5 | 1 | Type A | 67 | 178 | 155 | 44 | 335 | 957 | 1112 | 1156 | Floor | Minutes | Days
6 | 1 | Type A | 67 | 178 | 155 | 44 | 402 | 1135 | 1290 | 1334 | Floor 1 | 10334 | 21.5292
7 | 1 | Type A | 67 | 178 | 155 | 44 | 469 | 1313 | 1468 | 1512 | Floor 2 | 19543 | 40.7146
8 | 1 | Type A | 67 | 178 | 155 | 44 | 536 | 1491 | 1646 | 1690 | Floor 3 | 28752 | 59.9
9 | 1 | Type B | 225 | 599 | 524 | 150 | 761 | 2090 | 2614 | 2764 | Floor 4 | 37961 | 79.0854
10 | 1 | Type B | 225 | 599 | 524 | 150 | 986 | 2689 | 3213 | 3363 | Floor 5 | 47170 | 98.2708
11 | 1 | Type C | 353 | 941 | 823 | 235 | 1339 | 3630 | 4453 | 4688 | Floor 6 | 56379 | 117.4562
12 | 1 | Type C | 353 | 941 | 823 | 235 | 1692 | 4571 | 5394 | 5629
13 | 1 | Type C | 353 | 941 | 823 | 235 | 2045 | 5512 | 6335 | 6570
14 | 1 | Type C | 353 | 941 | 823 | 235 | 2398 | 6453 | 7276 | 7511
15 | 1 | Type C | 353 | 941 | 823 | 235 | 2751 | 7394 | 8217 | 8452
16 | 1 | Type C | 353 | 941 | 823 | 235 | 3104 | 8335 | 9158 | 9393
17 | 1 | Type C | 353 | 941 | 823 | 235 | 3457 | 9276 | 10099 | 10334
18 | 2 | Type A | 67 | 178 | 155 | 44 | 3524 | 9454 | 10254 | 10378
19 | 2 | Type A | 67 | 178 | 155 | 44 | 3591 | 9632 | 10409 | 10453
20 | 2 | Type A | 67 | 178 | 155 | 44 | 3658 | 9810 | 10564 | 10608
21 | 2 | Type A | 67 | 178 | 155 | 44 | 3725 | 9988 | 10719 | 10763
22 | 2 | Type A | 67 | 178 | 155 | 44 | 3792 | 10166 | 10874 | 10918
23 | 2 | Type A | 67 | 178 | 155 | 44 | 3859 | 10344 | 11029 | 11073
24 | 2 | Type A | 67 | 178 | 155 | 44 | 3926 | 10522 | 11184 | 11228
25 | 2 | Type A | 67 | 178 | 155 | 44 | 3993 | 10700 | 11339 | 11383
26 | 2 | Type B | 225 | 599 | 524 | 150 | 4218 | 11299 | 11863 | 12013
27 | 2 | Type B | 225 | 599 | 524 | 150 | 4443 | 11898 | 12422 | 12572
28 | 2 | Type C | 353 | 941 | 823 | 235 | 4796 | 12839 | 13662 | 13897
29 | 2 | Type C | 353 | 941 | 823 | 235 | 5149 | 13780 | 14603 | 14838
30 | 2 | Type C | 353 | 941 | 823 | 235 | 5502 | 14721 | 15544 | 15779
31 | 2 | Type C | 353 | 941 | 823 | 235 | 5855 | 15662 | 16485 | 16720
32 | 2 | Type C | 353 | 941 | 823 | 235 | 6208 | 16603 | 17426 | 17661
33 | 2 | Type C | 353 | 941 | 823 | 235 | 6561 | 17544 | 18367 | 18602
34 | 2 | Type C | 353 | 941 | 823 | 235 | 6914 | 18485 | 19308 | 19543
35 | 3 | Type A | 67 | 178 | 155 | 44 | 6981 | 18663 | 19463 | 19587
36 | 3 | Type A | 67 | 178 | 155 | 44 | 7048 | 18841 | 19618 | 19662
37 | 3 | Type A | 67 | 178 | 155 | 44 | 7115 | 19019 | 19773 | 19817
38 | 3 | Type A | 67 | 178 | 155 | 44 | 7182 | 19197 | 19928 | 19972
39 | 3 | Type A | 67 | 178 | 155 | 44 | 7249 | 19375 | 20083 | 20127
40 | 3 | Type A | 67 | 178 | 155 | 44 | 7316 | 19553 | 20238 | 20282
41 | 3 | Type A | 67 | 178 | 155 | 44 | 7383 | 19731 | 20393 | 20437
42 | 3 | Type A | 67 | 178 | 155 | 44 | 7450 | 19909 | 20548 | 20592
43 | 3 | Type B | 225 | 599 | 524 | 150 | 7675 | 20508 | 21072 | 21222
44 | 3 | Type B | 225 | 599 | 524 | 150 | 7900 | 21107 | 21631 | 21781
45 | 3 | Type C | 353 | 941 | 823 | 235 | 8253 | 22048 | 22871 | 23106
46 | 3 | Type C | 353 | 941 | 823 | 235 | 8606 | 22989 | 23812 | 24047
47 | 3 | Type C | 353 | 941 | 823 | 235 | 8959 | 23930 | 24753 | 24988
48 | 3 | Type C | 353 | 941 | 823 | 235 | 9312 | 24871 | 25694 | 25929
49 | 3 | Type C | 353 | 941 | 823 | 235 | 9665 | 25812 | 26635 | 26870
50 | 3 | Type C | 353 | 941 | 823 | 235 | 10018 | 26753 | 27576 | 27811
51 | 3 | Type C | 353 | 941 | 823 | 235 | 10371 | 27694 | 28517 | 28752
52 | 4 | Type A | 67 | 178 | 155 | 44 | 10438 | 27872 | 28672 | 28796
53 | 4 | Type A | 67 | 178 | 155 | 44 | 10505 | 28050 | 28827 | 28871
54 | 4 | Type A | 67 | 178 | 155 | 44 | 10572 | 28228 | 28982 | 29026
55 | 4 | Type A | 67 | 178 | 155 | 44 | 10639 | 28406 | 29137 | 29181
56 | 4 | Type A | 67 | 178 | 155 | 44 | 10706 | 28584 | 29292 | 29336
57 | 4 | Type A | 67 | 178 | 155 | 44 | 10773 | 28762 | 29447 | 29491
58 | 4 | Type A | 67 | 178 | 155 | 44 | 10840 | 28940 | 29602 | 29646
59 | 4 | Type A | 67 | 178 | 155 | 44 | 10907 | 29118 | 29757 | 29801
60 | 4 | Type B | 225 | 599 | 524 | 150 | 11132 | 29717 | 30281 | 30431
61 | 4 | Type B | 225 | 599 | 524 | 150 | 11357 | 30316 | 30840 | 30990
62 | 4 | Type C | 353 | 941 | 823 | 235 | 11710 | 31257 | 32080 | 32315
63 | 4 | Type C | 353 | 941 | 823 | 235 | 12063 | 32198 | 33021 | 33256
64 | 4 | Type C | 353 | 941 | 823 | 235 | 12416 | 33139 | 33962 | 34197
65 | 4 | Type C | 353 | 941 | 823 | 235 | 12769 | 34080 | 34903 | 35138
66 | 4 | Type C | 353 | 941 | 823 | 235 | 13122 | 35021 | 35844 | 36079
67 | 4 | Type C | 353 | 941 | 823 | 235 | 13475 | 35962 | 36785 | 37020
68 | 4 | Type C | 353 | 941 | 823 | 235 | 13828 | 36903 | 37726 | 37961
69 | 5 | Type A | 67 | 178 | 155 | 44 | 13895 | 37081 | 37881 | 38005
70 | 5 | Type A | 67 | 178 | 155 | 44 | 13962 | 37259 | 38036 | 38080
71 | 5 | Type A | 67 | 178 | 155 | 44 | 14029 | 37437 | 38191 | 38235
72 | 5 | Type A | 67 | 178 | 155 | 44 | 14096 | 37615 | 38346 | 38390
73 | 5 | Type A | 67 | 178 | 155 | 44 | 14163 | 37793 | 38501 | 38545
74 | 5 | Type A | 67 | 178 | 155 | 44 | 14230 | 37971 | 38656 | 38700
75 | 5 | Type A | 67 | 178 | 155 | 44 | 14297 | 38149 | 38811 | 38855
76 | 5 | Type A | 67 | 178 | 155 | 44 | 14364 | 38327 | 38966 | 39010
77 | 5 | Type B | 225 | 599 | 524 | 150 | 14589 | 38926 | 39490 | 39640
78 | 5 | Type B | 225 | 599 | 524 | 150 | 14814 | 39525 | 40049 | 40199
79 | 5 | Type C | 353 | 941 | 823 | 235 | 15167 | 40466 | 41289 | 41524
80 | 5 | Type C | 353 | 941 | 823 | 235 | 15520 | 41407 | 42230 | 42465
81 | 5 | Type C | 353 | 941 | 823 | 235 | 15873 | 42348 | 43171 | 43406
82 | 5 | Type C | 353 | 941 | 823 | 235 | 16226 | 43289 | 44112 | 44347
83 | 5 | Type C | 353 | 941 | 823 | 235 | 16579 | 44230 | 45053 | 45288
84 | 5 | Type C | 353 | 941 | 823 | 235 | 16932 | 45171 | 45994 | 46229
85 | 5 | Type C | 353 | 941 | 823 | 235 | 17285 | 46112 | 46935 | 47170
86 | 6 | Type A | 67 | 178 | 155 | 44 | 17352 | 46290 | 47090 | 47214
87 | 6 | Type A | 67 | 178 | 155 | 44 | 17419 | 46468 | 47245 | 47289
88 | 6 | Type A | 67 | 178 | 155 | 44 | 17486 | 46646 | 47400 | 47444
89 | 6 | Type A | 67 | 178 | 155 | 44 | 17553 | 46824 | 47555 | 47599
90 | 6 | Type A | 67 | 178 | 155 | 44 | 17620 | 47002 | 47710 | 47754
91 | 6 | Type A | 67 | 178 | 155 | 44 | 17687 | 47180 | 47865 | 47909
92 | 6 | Type A | 67 | 178 | 155 | 44 | 17754 | 47358 | 48020 | 48064
93 | 6 | Type A | 67 | 178 | 155 | 44 | 17821 | 47536 | 48175 | 48219
94 | 6 | Type B | 225 | 599 | 524 | 150 | 18046 | 48135 | 48699 | 48849
95 | 6 | Type B | 225 | 599 | 524 | 150 | 18271 | 48734 | 49258 | 49408
96 | 6 | Type C | 353 | 941 | 823 | 235 | 18624 | 49675 | 50498 | 50733
97 | 6 | Type C | 353 | 941 | 823 | 235 | 18977 | 50616 | 51439 | 51674
98 | 6 | Type C | 353 | 941 | 823 | 235 | 19330 | 51557 | 52380 | 52615
99 | 6 | Type C | 353 | 941 | 823 | 235 | 19683 | 52498 | 53321 | 53556
100 | 6 | Type C | 353 | 941 | 823 | 235 | 20036 | 53439 | 54262 | 54497
101 | 6 | Type C | 353 | 941 | 823 | 235 | 20389 | 54380 | 55203 | 55438
102 | 6 | Type C | 353 | 941 | 823 | 235 | 20742 | 55321 | 56144 | 56379